## Sheet1
Parking Garage | Planned |  | Actual |  | References
| Start Date | End Date | Start Date | End Date
Setup SVN/Github |  |  |  | 2014-10-02 | http://www.cs.colostate.edu/~ghosh/courses/cs414-f14/yr2014fa/home_resources.php
Check in existing diagrams: Use Cases, Domain Model, A2, A3 |  |  |  | 2014-10-02 | http://www.cs.colostate.edu/~ghosh/courses/cs414-f14/yr2014fa/home_resources.php
Identify sequence diagrams | 2014-10-03 | 2014-10-03
Draw SD 1 | 2014-10-04 | 2014-10-04
Draw SD 2 | 2014-10-05 | 2014-10-05
Draw SD 3 | 2014-10-06 | 2014-10-06
Prepare Design Class Diagram | 2014-10-04 | 2014-10-07
Plan out Test Plan | 2014-10-21 | 2014-10-22 |  |  | http://www.cs.colostate.edu/~ghosh/courses/cs414-f14/yr2014fa/more_assignments/TestPlan.php
Write up Test Cases in Test Plan | 2014-10-23 | 2014-10-25
Study GRASP patterns if not yet done | 2014-10-04 | 2014-10-04
Identify/Create Controller | 2014-10-09 | 2014-10-09
Create skeleton classes/methods | 2014-10-08 | 2014-10-09
Create Junit test cases for operations identified in Class Diagram | 2014-10-10 | 2014-10-10
Write implementation of test cases | 2014-10-11 | 2014-10-15
Write code in skeleton classes | 2014-10-16 | 2104-10-20
Revise | 2014-10-26 | 2014-10-29